Ai Governance 30-Day Plan

Version 1.0 · Last updated 2026-09-11

Informational only, not legal advice. Completing this file does not make an organisation compliant with any law or standard. AIPolicyTracker (aipolicytracker.org), CC BY 4.0.

| nist-ai-rmf | Week | Goal | Tasks | Output | NIST AI RMF function |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Know what you have | Appoint the owner; fill the AI System Inventory Template; decide your role per system; list applicable laws per market | Inventory v1 | Govern, Map |
| Week 2 | Know what could go wrong | Fill the AI Risk Register Template for production systems; screen prohibited practices; classify EU AI Act risk | Risk register v1; screening record | Map, Measure |
| Week 3 | Decide how you work | Write a two-page AI policy (acceptable use, approval, oversight, vendor rules); set review cadence; run an incident tabletop with the AI Incident Response Checklist | AI policy; incident procedure | Govern, Manage |
| Week 4 | Show the evidence | Assemble the evidence pack (inventory, register, policy, tests, approvals); complete the EU AI Act Readiness Checklist gaps list; plan the next quarter | Evidence pack; gap plan | Manage |
| Day 30 | Review | Leadership review: risks accepted, budget for gaps, owners confirmed, next review date set | Signed review note | Govern |

Informational only, not legal advice. AIPolicyTracker (aipolicytracker.org), CC BY 4.0.