## AI incident response
Ai Incident Response — AIPolicyTracker free template
Version 1.0 · Last updated 2026-09-11
Informational only, not legal advice. Completing this file does not make an organisation compliant with any law or standard. AIPolicyTracker (aipolicytracker.org), CC BY 4.0.
Stage | Item | Owner | Time target | Reference | Done
Prepare | Define what counts as an AI incident (harm, near-miss, policy breach, model drift) and severity levels | Governance lead | Before go-live | Internal policy; NIST AI RMF MANAGE 4 | No
Prepare | Maintain a notification matrix: regulator, data-protection authority, customers, insurer, press | Governance lead | Before go-live | EU AI Act Art. 73; GDPR Art. 33 | No
Prepare | Enable a kill switch / human-only mode and a tested rollback per system | Technical owner | Before go-live | EU AI Act Art. 14 | No
Detect | Monitor user reports, output audits, drift metrics, abuse signals and press mentions | On-call | Continuous | ISO/IEC 42001 monitoring | No
Triage | Classify the incident by MIT AI Risk Repository domain, affected people and severity | Incident lead | 1 hour | Internal severity scale | No
Contain | Stop or restrict the system, preserve logs and prompts, snapshot the model version | Technical owner | 2 hours | EU AI Act Art. 12 logging | No
Notify | Report serious incidents to the market-surveillance authority within the statutory deadline; data breaches within 72 hours | Legal / DPO | Per deadline | EU AI Act Art. 73; GDPR Art. 33 | No
Notify | Inform affected users and customers with plain-language guidance | Communications | 24 hours | Contractual; consumer law | No
Recover | Fix, re-test (including red-team), decide re-deployment with sign-off | Technical owner | Per severity | EU AI Act Art. 15 | No
Learn | Post-incident review; update risk register, controls, training and this checklist | Governance lead | 10 days | NIST AI RMF MANAGE; ISO/IEC 42001 improvement | No